## Deliverable
Deliverable Name | Description | Complexity | Estimated Hours | Hours Used | Hours Remaining | Workday Remaining | Status | Notes
Abbreviation Dictionary | Creation of the initial CSV dictionary for path abbreviations. | Low | T&M |  |  |  | Not Started | Basis for the script's abbreviation logic, requires manual creation
Script Development | Development of the Python script for path shortening, including reading config files and executing abbreviation logic. | High | 40 | 16 | 24 | 3 | In Progress
Error Handling Mechanism | Implementation of error handling and logging within the script. | Medium | 8 | 0 | 8 | 1 | In Progress
Conflict Resolution Logic | Development of logic to handle file name conflicts during the abbreviation process. | Medium | 8 | 0 | 8 | 1 | Done | Include a re-try mechanism for new file/folder name in case of naming conflict
Testing & QA Reports | Conducting a thorough and streamlined testing process, including local testing and collaborative testing with intended users. 1. Create testing env, replicate/simulate target sys (4 hours) 2. Test in larger scale ( 4 hours) 3. Test all the features in the scripts, both happy path and not happy path (8 hours) 4. Test error handling (8 hours) 5. Test features in target env (with mock data) (8 hours) | High | 32 | 8 | 24 | 3 | In Progress
User Manual & Documentation | Comprehensive user manual and documentation, covering installation, usage, and troubleshooting. | Medium | 16 | 0 | 16 | 2 | Not Started
Knowledge Transfer Material | Preparation of presentation slides and demo scripts for knowledge transfer sessions. | Low | 5 | 0 | 5 | 0.625 | Not Started
Script Validation and Handover | Ensure script validation and handover is expected | Low | 4 | 0 | 4 | 0.5 | Not Started
Post Migration Support | Support to first usage of the script | Low | TBD |  |  |  | Not Started

## Features
Feature Name | Description | Status | Notes
CSV Dictionary Loading | Functionality to load and parse the CSV abbreviation dictionary. A CSV dictionary which is a key-value pair CSV, it will contain entries like: product, prod project, proj | Not Started
Path Scanning | Scans directories for files with paths or filenames exceeding the length limit. 1. Configurable length threshold 2. Output scan result | Completed
Abbreviation Logic | 1.1 Analyze the filename form: random string, delimited (underscore, hyphen, both?), camelCase 1.2 Based on different format, attemp to breakdown the filename into component, for each component, check if the dictionary has a key for its conversion, if yes, convert it. For example, if the filename is productproject123.txt, the script should recongize that it has no known delimiter and is not in camelCase, so it is the random string type, then it will use the random string type conversion flow to attemp to shorten the file path. 1.3 If conversion is sucessful, log it in the output file, long_filename_modified_output 1.4 If a conversion is not possible, log it in the error output file, long_filename_modified_error | In Progress | 1. The filename can be in different form. We will assume it will be one of the following: 1.1 Filename will be in random string, no visible delimiter. For example, productproject123.txt 1.2 Filename will be delimited a combination of underscore or hyphen. For example, product_project_123.pdf, product-project-123.pdf, product-project-ver_1.pdf 1.3 Filename will be in camelCase. For example, productProject123.txt 2. Here are the conversion flow based on the filename naming type: 2.1 Random string: So filename under this type has no known delimiter and is not in camelCase. The script should try to use the keys in dictionary as substring and try to see if they exist in the filename. For example: productproject123.txt should be renamed to prodproj123.txt because we have product, prod and project, proj in our dictionary. However, abcd1234.txt should not be able to convert because we have no key in the dictionary that is a substring of the filename. 2.2 Delimited by known delimiter: Filenames under this type will contain known delimiters, such as underscore and/or hyphen. For example, product_project_123.pdf, product-project-123.pdf, product-project-ver_1.pdf. The script should attemp to breakdown the filename into different components, then use the dictionary to see if a conversion is possible. For example, if the filename is product-project-ver_1.pdf, then the script should break it down to product, project, ver, 1.pdf and convert the filename to prod-proj-ver_1.pdf because we have product, project as keys, but not ver or 1.pdf, they are not found as key in the dictionary.
Error Handling | Robust error handling for file operations and exceptions. 1. File not found 2. File being used 3. File/folder being locked | In Progress
Logging Mechanism | Implements logging for actions taken and errors encountered. 1. Logging for processed filepath and filenames. 2. Logging for filepath or filenames that failed to process | In Progress
Config Mechanism | Enable using external file to config various part of the script | In Progress
Batching Mechanism | 1. Enable batching for scanning folders 2. Enable batching for shoterning process | Not Started
Conflict Resolution | Logic to handle potential file name conflicts during abbreviation. | Not Started | Before the actual rename, the script should check, if there is a file name conflict. For example, if the new file name is prod-proj-ver_1.pdf, but such file already exist in the target folder, then the script should note there is a file naming conflict in the log, then try to rename it by appending _1 to the end of the filename. If _1 is taken, then increment to _2, _3 and so on, until a valid name is found. (limit the retry to 10, if fail to rename, log it)
Testing & Documentation | Testing each feature and preparing documentation. | Not Started

## Estimated Timeline
Date | Planned Task | Task Requirements
2024-01-29 | Script Development-3
2024-01-30 | Script Development-4
2024-01-31 | Script Development-5
2024-02-01 | Error Handling Mechanism-1
2024-02-02 | User Manual & Documentation-1
2024-02-03 | N/A - Weekend
2024-02-04 | N/A - Weekend
2024-02-05 | Testing-2 | Testing on target system using mock data: 1. Restore a drop to a test envirnoment that is permitted to test (delete or rename without consequence) 2. The data size should be close to real situation. Ensure the data set can satisfy both use cases: long nested-folders and long filenames 3. Same user account/type as the one will be used on the script
2024-02-06 | Testing-3
2024-02-07 | Testing-4
2024-02-08 | User Manual & Documentation-2
2024-02-09 | Knowledge Transfer Material Script Validation and Handover
2024-02-10 | N/A - Weekend
2024-02-11 | N/A - Weekend
2024-02-12
2024-02-13
2024-02-14
2024-02-15
2024-02-16
2024-02-17 | N/A - Weekend
2024-02-18 | N/A - Weekend